## Sprint Backlog
Sprint Backlog
| PROJECT NAME | Team Leader | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
| Hospital Management System | Mila Hoogstraat | 2019-03-04 | 2004-12-19 |  | 100%
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
Iteration 1
| Login | Programmable(?) | Yushae |  | 2019-03-04 | 2019-03-06 | 2 | Completed | Able to login
| User Stories | Documentation(?) | Mila |  |  |  | 1 | Completed | Updated set of user stories promised
| Register | Programmable(?) | Yushae |  | 2019-03-04 | 2019-03-06 | 2 | Completed | Able to register
Iteration 2
| Book Appointment | Programmable(?) | Yushae(backend),Neilson(Frontend) |  | 2019-03-13 | 2019-03-17 | 4 | Completed | Appointment times cannot conflict
| View Appointment | Programmable(?) | Nandakumar |  | 2019-03-17 | 2019-03-17 | 1 | Completed | Users now able to view their own schedule
| Make Doctors Account | Programmable(?) | Yushae |  | 2019-03-12 | 2019-03-12 | 1 | Completed | Doctors may now register for a Doctor account
| Make Admin Account | Programmable(?) | Yushae |  | 2019-03-12 | 2019-03-12 | 1 | Completed | Admins can create their own accounts
| Menu | Programmable(?) | Dom,Yushae |  | 3-14-19 | 3-14-19 |  | Completed | Menu now available for easy navigation
| Change Password | Programmable(?) | Nielson |  | 2019-03-16 | 2019-03-16 | 1 | Completed | Users a now able to change their password from the website however visual feedback has yet to be implemented
Iteration 3
| Create, Modify and delete patient profiles | Programmable(?) | Yushae |  | 2019-03-20 | 2019-03-22 | 2 | Complete | Admin can now modify profiles
| create, modify and delete doctor/nurse schedules | Programmable(?) | Yushae |  | 2019-03-24 | 3-25-19 | 1 | Complete | Admin can now modify profiles
| Final | - | - |  | - | - | - | N/A | -